## Data (hidden)
| Score | Outputs |  | EXECUTED | ON | NOT DONE
| YES |  | 2021-01-01
| ON |  | 2021-02-01 | 0% | 0% | 100%
| NO |  | 2021-03-04 | 0% | 0% | 100%
|  |  | 2021-04-04 | 0% | 0% | 100%
2021-05-05
Completed |  |  | 2021-06-05 | 0% | 100% | 0%
In Progress |  |  | 2021-07-06 | 0% | 100% | 0%
Not done |  |  | 2021-08-06
N/A |  |  | 2021-09-06
|  |  | 2021-10-07 | 0% | 0% | 0%
2021-11-07
2021-12-08
2022-01-08
2022-02-08
2022-03-11
Activities
|  |  |  | PLANNED | EXECUTED | ON | NOT DONE
|  |  | 2021-01-01 | 0 | 0 | 0 | 0
|  |  | 2021-02-01 | 1 | 0 | 0 | 1
|  |  | 2021-03-04 | 1 | 0 | 0 | 1
|  |  | 2021-04-04 | 1 | 0 | 0 | 1
|  |  | 2021-05-05 | 0 | 0 | 0 | 1
|  |  | 2021-06-05 | 1 | 0 | 1 | 0
|  |  | 2021-07-06 | 1 | 0 | 1 | 0
|  |  | 2021-08-06 | 0 | 1 | 0 | 0
|  |  | 2021-09-06 | 0 | 0 | 0 | 0
|  |  | 2021-10-07 | 1 | 0 | 0 | 0
|  |  | 2021-11-07 | 0 | 0 | 0 | 0
|  |  | 2021-12-08 | 0 | 0 | 0 | 0
|  |  | 2022-01-08 | 0 | 0 | 0 | 0
|  |  | 2022-02-08 | 0 | 0 | 0 | 0
|  |  | 2022-03-11 | 0 | 0 | 0 | 0
Milestones
|  |  | Completed | 0
|  |  | In-Progress | 1
|  |  | Not Done | 1
|  |  |  | Completed | In-Progress | Not Done
|  |  | Increased ANC attendance | 0 | 1 | 1
|  |  | Reduced teenage pregnancies | 0 | 0 | 0
|  |  | Increased Referrals | 0 | 0 | 0
|  |  |  | Completed | In-Progress | Not Done
|  |  | Increased ANC attendance | 0% | 50% | 50%
|  |  | Reduced teenage pregnancies | #DIV/0! | #DIV/0! | #DIV/0!
|  |  | Increased Referrals | #DIV/0! | #DIV/0! | #DIV/0!

## Guide
COALITION OPERATIONS TRACKING TOOL (COTT) GUIDE
Filling the tool: At Planning
1. Start with the sheet labelled "Priority_Results tracker" to define your desired results, problems, indicators, milestones, timelines, responsibilities and means of verification. 2. Proceed to the sheet labelled "Work plan Gantt" to specify your activities/tasks for each result area including responsibilities, budget and schedules 3. Change the start date only at one point in Cell AP1 of the sheet labelled "Work plan Gantt". It is Highligeted in Green colour. The Rest will auto-populate as they are controlled by formula 4. DO NOT TOUCH the sheets labelled "Activity_milestones_Status" and "DASHBOARD" at this stage. They are controlled by formulas fully
Filling the tool: During implementation
1. During implementation, on a monthly basis, Check the activities that were due for implementation that month as per schedules in columns H-V of the "Work Plan Gantt" sheet. Proceed and update the progress area in Columns Y-AM of the same sheet. Do that by selecting from the drop down menuwhether or not the activity has been implemented or On going. Also indicate the amount spent against each activity as per plan in column AN 2. Activities are linked to result areas in the sheet labelled "Priority_Results tracker". Indicate by typing in what you have accomplished that contributes to the milestone specified in column N of the same sheet. These are called Activity Outputs to the milestones. Indicate them by typing against the relevant month and milestone area in column T through to AH 3. Select the Status of completion of each milestone in column R of the sheet labelled "Priority_Results tracker". Indicate by selecting from the drop dowm menu whether the milestone achievement is completed, on-going or not done 4. DO NOT TOUCH Columns AZ-BT of the sheet labelled "Priority_Results tracker". They are controlled by formulas fully
Progress reports

## Work plan Gantt
S/N | Result code | Activities | Response area |  |  |  | Schedule | [14 empty] | Progress | [14 empty] | Cummulative budget absorbed | Activity progress comments
|  |  |  | Location | Activity Lead | Budget | 2021-01-01 | 2021-02-01 | 2021-03-04 | 2021-04-04 | 2021-05-05 | 2021-06-05 | 2021-07-06 | 2021-08-06 | 2021-09-06 | 2021-10-07 | 2021-11-07 | 2021-12-08 | 2022-01-08 | 2022-02-08 | 2022-03-11 | 2021-01-01 | 2021-02-01 | 2021-03-04 | 2021-04-04 | 2021-05-05 | 2021-06-05 | 2021-07-06 | 2021-08-06 | 2021-09-06 | 2021-10-07 | 2021-11-07 | 2021-12-08 | 2022-01-08 | 2022-02-08 | 2022-03-11
1 | 1 | Insert you activity here | ANC | Insert Location here | Insert initials |  |  | Yes | [14 empty] | NO | NO | NO | NO | ON | ON | YES
2 | 1.1 | Insert you activity here | MPDSR | Insert Location here | Insert initials | 12000 |  |  |  | Yes | [26 empty] | 11000
3 | 1 | Insert you activity here | FP | Insert Location here | Insert initials | 30000 |  |  | Yes | [27 empty] | 30000
4 | 1 | Insert you activity here | MPDSR | Insert Location here | Insert initials | 0 | [5 empty] | Yes
5 | 1.1 | Insert you activity here | FP | Insert Location here | Insert initials | 10000 | [9 empty] | Yes | [20 empty] | 4000
TOTAL | [5 empty] | 52000 | 0 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45000
[22 empty] | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Formulas:
Progress = [Schedule]
Note on H1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Put "Yes" where applicable to colour
Note on Y1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Select status from the drop down menu

## Priority_Results tracker
Code | Coalition Priorities | [7 empty] | Status |  | Progress Status Notes | [30 empty] | Work plan | [5 empty] | Timelines Progress
| Desired Result |  | Problem | Result/Indicator | Milestone(s) | Timeline | Lead Organization/Person | Means of verification | Reporting period |  | 2021-01-01 | 2021-02-01 | 2021-03-04 | 2021-04-04 | 2021-05-05 | 2021-06-05 | 2021-07-06 | 2021-08-06 | 2021-09-06 | 2021-10-07 | 2021-11-07 | 2021-12-08 | 2022-01-08 | 2022-02-08 | 2022-03-11 | 2022-04-11 | 2022-05-12 | 2022-06-12 | 2022-07-13 | 2022-08-13 | 2022-09-13 | 2022-10-14 | 2022-11-14 | 2022-12-15 | 2023-01-15 | 2023-02-15 | 2023-03-18 | 2023-04-18 | 2023-05-19 | 2023-06-19 | 2023-07-20 | Activities | Owner | Budget | Absorbed | Balance/Surplus/Deficit | % absorption | 2021-01-01 | 2021-02-01 | 2021-03-04 | 2021-04-04 | 2021-05-05 | 2021-06-05 | 2021-07-06 | 2021-08-06 | 2021-09-06 | 2021-10-07 | 2021-11-07 | 2021-12-08 | 2022-01-08 | 2022-02-08 | 2022-03-11
1 | Increased ANC attendance | [7 empty] | In Progress | n | 2021-01-01: Insert your notes here | Insert you activity here | Insert initials |  |  |  |  | n | n | n | n | n | n | n | n | n | n | n | n | n | n | n
[42 empty] | Insert you activity here | Insert initials | 12000 | 11000 | 1000 | 91.67% | n | n | n | n | n | n | n | n | n | n | n | n | n | n | n
[42 empty] | Insert you activity here | Insert initials | 30000 | 30000 | 0 | 100% | n | n | n | n | n | n | n | n | n | n | n | n | n | n | n
[42 empty] | Insert you activity here | Insert initials |  |  |  |  | n | n | n | n | n | n | n | n | n | n | n | n | n | n | n
[42 empty] | Insert you activity here | Insert initials | 10000 | 4000 | 6000 | 40% | n | n | n | n | n | n | n | n | n | n | n | n | n | n | n
[48 empty] | n | n | n | n | n | n | n | n | n | n | n | n | n | n | n
[48 empty] | n | n | n | n | n | n | n | n | n | n | n | n | n | n | n
1.1 |  | Increase early attendance for 1st ANC (Before 16 weeks (4 months) of gestation) | [6 empty] | Not done | n | [37 empty] | n | n | n | n | n | n | n | n | n | n | n | n | n | n | n
[48 empty] | n | n | n | n | n | n | n | n | n | n | n | n | n | n | n
[48 empty] | n | n | n | n | n | n | n | n | n | n | n | n | n | n | n
[48 empty] | n | n | n | n | n | n | n | n | n | n | n | n | n | n | n
[48 empty] | n | n | n | n | n | n | n | n | n | n | n | n | n | n | n
[48 empty] | n | n | n | n | n | n | n | n | n | n | n | n | n | n | n
[48 empty] | n | n | n | n | n | n | n | n | n | n | n | n | n | n | n
1.1.1 | [9 empty] | n | [37 empty] | n | n | n | n | n | n | n | n | n | n | n | n | n | n | n
[48 empty] | n | n | n | n | n | n | n | n | n | n | n | n | n | n | n
1.1.2 | [9 empty] | n | [37 empty] | n | n | n | n | n | n | n | n | n | n | n | n | n | n | n
[48 empty] | n | n | n | n | n | n | n | n | n | n | n | n | n | n | n
[48 empty] | n | n | n | n | n | n | n | n | n | n | n | n | n | n | n
[48 empty] | n | n | n | n | n | n | n | n | n | n | n | n | n | n | n
1.1.3 | [9 empty] | n | [37 empty] | n | n | n | n | n | n | n | n | n | n | n | n | n | n | n
[48 empty] | n | n | n | n | n | n | n | n | n | n | n | n | n | n | n
1.2 |  | Intensifying Community referral systems through CHS | [7 empty] | n | [37 empty] | n | n | n | n | n | n | n | n | n | n | n | n | n | n | n
[48 empty] | n | n | n | n | n | n | n | n | n | n | n | n | n | n | n
[48 empty] | n | n | n | n | n | n | n | n | n | n | n | n | n | n | n
[48 empty] | n | n | n | n | n | n | n | n | n | n | n | n | n | n | n
[48 empty] | n | n | n | n | n | n | n | n | n | n | n | n | n | n | n
[48 empty] | n | n | n | n | n | n | n | n | n | n | n | n | n | n | n
[48 empty] | n | n | n | n | n | n | n | n | n | n | n | n | n | n | n
1.2.1 | [9 empty] | n | [37 empty] | n | n | n | n | n | n | n | n | n | n | n | n | n | n | n
[48 empty] | n | n | n | n | n | n | n | n | n | n | n | n | n | n | n
1.2.2 | [9 empty] | n | [37 empty] | n | n | n | n | n | n | n | n | n | n | n | n | n | n | n
[48 empty] | n | n | n | n | n | n | n | n | n | n | n | n | n | n | n
1.2.3 | [9 empty] | n | [37 empty] | n | n | n | n | n | n | n | n | n | n | n | n | n | n | n
[48 empty] | n | n | n | n | n | n | n | n | n | n | n | n | n | n | n
[48 empty] | n | n | n | n | n | n | n | n | n | n | n | n | n | n | n
[48 empty] | n | n | n | n | n | n | n | n | n | n | n | n | n | n | n
[48 empty] | n | n | n | n | n | n | n | n | n | n | n | n | n | n | n
2 | Reduced teen pregnancies | [8 empty] | n | [37 empty] | n | n | n | n | n | n | n | n | n | n | n | n | n | n | n
[48 empty] | n | n | n | n | n | n | n | n | n | n | n | n | n | n | n
[48 empty] | n | n | n | n | n | n | n | n | n | n | n | n | n | n | n
[48 empty] | n | n | n | n | n | n | n | n | n | n | n | n | n | n | n
2.1 | [9 empty] | n | [37 empty] | n | n | n | n | n | n | n | n | n | n | n | n | n | n | n
[48 empty] | n | n | n | n | n | n | n | n | n | n | n | n | n | n | n
[48 empty] | n | n | n | n | n | n | n | n | n | n | n | n | n | n | n
[48 empty] | n | n | n | n | n | n | n | n | n | n | n | n | n | n | n
[48 empty] | n | n | n | n | n | n | n | n | n | n | n | n | n | n | n
[48 empty] | n | n | n | n | n | n | n | n | n | n | n | n | n | n | n
[48 empty] | n | n | n | n | n | n | n | n | n | n | n | n | n | n | n
[48 empty] | n | n | n | n | n | n | n | n | n | n | n | n | n | n | n
[48 empty] | n | n | n | n | n | n | n | n | n | n | n | n | n | n | n
[48 empty] | n | n | n | n | n | n | n | n | n | n | n | n | n | n | n
[48 empty] | n | n | n | n | n | n | n | n | n | n | n | n | n | n | n
[48 empty] | n | n | n | n | n | n | n | n | n | n | n | n | n | n | n
[48 empty] | n | n | n | n | n | n | n | n | n | n | n | n | n | n | n
[48 empty] | n | n | n | n | n | n | n | n | n | n | n | n | n | n | n
[48 empty] | n | n | n | n | n | n | n | n | n | n | n | n | n | n | n
2.1.1 | [9 empty] | n | [37 empty] | n | n | n | n | n | n | n | n | n | n | n | n | n | n | n
[48 empty] | n | n | n | n | n | n | n | n | n | n | n | n | n | n | n
2.1.2 | [9 empty] | n | [37 empty] | n | n | n | n | n | n | n | n | n | n | n | n | n | n | n
[48 empty] | n | n | n | n | n | n | n | n | n | n | n | n | n | n | n
2.1.3 | [9 empty] | n | [37 empty] | n | n | n | n | n | n | n | n | n | n | n | n | n | n | n
[48 empty] | n | n | n | n | n | n | n | n | n | n | n | n | n | n | n
2.2. | [9 empty] | n | [37 empty] | n | n | n | n | n | n | n | n | n | n | n | n | n | n | n
[48 empty] | n | n | n | n | n | n | n | n | n | n | n | n | n | n | n
2.2.1 | [9 empty] | n | [37 empty] | n | n | n | n | n | n | n | n | n | n | n | n | n | n | n
3 | Increased Referral services | [8 empty] | n | [37 empty] | n | n | n | n | n | n | n | n | n | n | n | n | n | n | n
3.1 | [9 empty] | n | [37 empty] | n | n | n | n | n | n | n | n | n | n | n | n | n | n | n
[48 empty] | n | n | n | n | n | n | n | n | n | n | n | n | n | n | n
[48 empty] | n | n | n | n | n | n | n | n | n | n | n | n | n | n | n
[48 empty] | n | n | n | n | n | n | n | n | n | n | n | n | n | n | n
[48 empty] | n | n | n | n | n | n | n | n | n | n | n | n | n | n | n
3.1.1 | [9 empty] | n | [37 empty] | n | n | n | n | n | n | n | n | n | n | n | n | n | n | n
[48 empty] | n | n | n | n | n | n | n | n | n | n | n | n | n | n | n
[48 empty] | n | n | n | n | n | n | n | n | n | n | n | n | n | n | n
[48 empty] | n | n | n | n | n | n | n | n | n | n | n | n | n | n | n
[48 empty] | n | n | n | n | n | n | n | n | n | n | n | n | n | n | n
3.2 | [9 empty] | n | [37 empty] | n | n | n | n | n | n | n | n | n | n | n | n | n | n | n
[48 empty] | n | n | n | n | n | n | n | n | n | n | n | n | n | n | n
[48 empty] | n | n | n | n | n | n | n | n | n | n | n | n | n | n | n
[48 empty] | n | n | n | n | n | n | n | n | n | n | n | n | n | n | n
[10 empty] | n | [37 empty] | n | n | n | n | n | n | n | n | n | n | n | n | n | n | n
3.2.1 | [47 empty] | n | n | n | n | n | n | n | n | n | n | n | n | n | n | n
Note on U73: Windows User: Did this happen? When?

## Refined_progress (hidden)
SN | Code | Activity | 2021-01-01 | 2021-02-01 | 2021-03-04 | 2021-04-04 | 2021-05-05 | 2021-06-05 | 2021-07-06 | 2021-08-06 | 2021-09-06 | 2021-10-07 | 2021-11-07 | 2021-12-08 | 2022-01-08 | 2022-02-08 | 2022-03-11 | Type | Location | Activity owner | Budget | Absorbed
1 | 1 | Insert you activity here |  | NO | NO | NO | NO | ON | ON | YES | [7 empty] | ANC | Insert Location here | Insert initials | 0
2 | 1.1 | Insert you activity here | [15 empty] | MPDSR | Insert Location here | Insert initials | 12000 | 11000
3 | 1 | Insert you activity here | [15 empty] | FP | Insert Location here | Insert initials | 30000 | 30000
4 | 1 | Insert you activity here | [15 empty] | MPDSR | Insert Location here | Insert initials | 0
5 | 1.1 | Insert you activity here | [15 empty] | FP | Insert Location here | Insert initials | 10000 | 4000
TOTAL

## Activity_milestones_Status
S/N | RF code | Activities | Type | Location | Activity owner | Budget | Schedule | [14 empty] | Progress | [15 empty] | Status |  | Comments/ Steps to milestone
[7 empty] | 2021-01-01 | 2021-02-01 | 2021-03-04 | 2021-04-04 | 2021-05-05 | 2021-06-05 | 2021-07-06 | 2021-08-06 | 2021-09-06 | 2021-10-07 | 2021-11-07 | 2021-12-08 | 2022-01-08 | 2022-02-08 | 2022-03-11 | 2021-01-01 | 2021-02-01 | 2021-03-04 | 2021-04-04 | 2021-05-05 | 2021-06-05 | 2021-07-06 | 2021-08-06 | 2021-09-06 | 2021-10-07 | 2021-11-07 | 2021-12-08 | 2022-01-08 | 2022-02-08 | 2022-03-11 | Milestone
1 | 1 | Insert you activity here | ANC | Insert Location here | Insert initials | 0 |  | Yes | [13 empty] | 2021-02-01: NO; 2021-03-04: NO; 2021-04-04: NO; 2021-05-05: NO; 2021-06-05: ON; 2021-07-06: ON; 2021-08-06: YES |  | In Progress | n | Insert your notes here
2 | 1.1 | Insert you activity here | MPDSR | Insert Location here | Insert initials | 12000 |  |  |  | Yes
3 | 1 | Insert you activity here | FP | Insert Location here | Insert initials | 30000 |  |  | Yes
4 | 1 | Insert you activity here | MPDSR | Insert Location here | Insert initials | 0 | [5 empty] | Yes
5 | 1.1 | Insert you activity here | FP | Insert Location here | Insert initials | 10000 | [9 empty] | Yes
[38 empty] | Not done | n
[38 empty] | 0 | n
[38 empty] | 0 | n
[38 empty] | 0 | n
[38 empty] | 0 | n
[22 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | n
[22 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[38 empty] | 0 | n
[38 empty] | 0 | n
[38 empty] | 0 | n
[38 empty] | 0 | n
[38 empty] | 0 | n
[38 empty] | 0 | n
[38 empty] | 0 | n
[38 empty] | 0 | n
[38 empty] | 0 | n
[38 empty] | 0 | n
[38 empty] | 0 | n
[38 empty] | 0 | n
[38 empty] | 0 | n
TOTAL | [6 empty] | 0 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | [31 empty] | 0 | n
|  |  | 0 | 0 | 0 | 0
Note on AY17: Windows User: How will this be achieved this reporting period when activities are scheduled next period?

## DASHBOARD
| FUNDS REQUIRED |  | EXPENDITURE |  | EXP. RATE
Increased ANC attendance
|  | 52000 |  | 45000 |  | 86.5%
Reduced teen pregnancies
|  | 0 |  | 0 |  | #DIV/0!
Increased Referral services
|  | 0 |  | 0 |  | #DIV/0!
KES 52,000
86.5%
#DIV/0!
#DIV/0!
KES -
KES -
KES 45,000
KES -
KES -

## Deatiled Budget
[9 empty] | Quarter 1 |  |  | Quarter 2 |  |  | Quarter 3 |  |  | Quarter 4
S/N | RF Code | Activity | Costing detail | Unit of measure | Units | Frequency | Unit cost | Total | 2021-01-01 | 2021-02-01 | 2021-03-04 | 2021-04-04 | 2021-05-05 | 2021-06-05 | 2021-07-06 | 2021-08-06 | 2021-09-06 | 2021-10-07 | 2021-11-07 | 2021-12-08
1 | 1 | Validation of Scorecard | Conference package-Full day | pax | 30 | 1 | 4500 | 135000 |  |  | 33750 |  |  | 33750
|  |  | Transport | Pax | 30 | 1 | 1000 | 30000
|  |  | Printing | Pax | 30 | 1 | 200 | 6000
Sub total | [7 empty] | 171000

## Budget summaries
171000